## Sheet1
OCM Tidy Up | Issue/Action | Additional Comments | MRN
Patient History | Remove
OCM BT | Remove
Batch request | Remove | when was this deployed
Critical List | Remove | when was this deployed
Messaging | Remove | when was this deployed
Patient Aduit | Remove
User mapping | Remove
User Levels | Remove | Who can see results etc
Issues with OCM
Ward Requiry | External results not displaying for both OCM and paper request |  | 253829
| External results list only shows paper requests sampleID | Does this list pull everything on the patient or just 35 days. | 253829
| External and Biochemistry Cumulative | Shows the external results | 253829
| View Scan for paper externals | Not functioning | 253829
Download report on OCM numbers not working
| View Request not working | What is it, what is it suppose to do.
| Speed Issue | Cumulatives especially | 105870
| Printed Report | No functionality to print | 253829
| BT Cumulative Remove from dropdown | Remove, this is not working | 253829
| Remove ALL from cumulative dropdown | Remove, this is not working | 253829
Labels
Issue with browser settings
01DDMMYY
| Reprint labels does not open print review. Ctrl +P | Should not be able to reprint labels in OCM, functioality should only be in LIMS
Sample Collection
| Back button on Phlebotomy page | Not taking the user back to the collection list.
| Issues with speed of printing | taking too long to go from Generate barcode to print preview
| Issues with scanning Barcodes | barcode already scanned error message
Log in
Log in on another device when user is not
LIMS
| Scanning in of SampleID | Extremely slow. SampleId 90007816 FBC after 5 minutes of spinning. Refresh screen and scanned again
| Delay in requests going into AMS and EPU | takes up to 20 minutes
| OCM externals | Having to print an external form for Biomnis
Scan Request
| OCM paper request form CC duplicate GP | Ticket raised 90007816