## Cavan
Client Name | Application | Ticket No. | Ticket Date | Ticket Comp Date | Ticket Close Date | Description | Current Version | Change to Version | Exe Sent Date | Changes | Change Date | Develepor Name | Development Date | Specimen numbers | Tester Name | Tested Date | Appendicies
Cavan | Net Acquire | 6579dbdeef522 | 2023-12-13 | 2023-12-15 |  | Unable to print haem report because GP field populated with 0 | 6.12.145 | 6.12.146 | 2023-12-17 | wrote a function that will go to DB of demographics check the GP Details if there are any and will populate in the required Field+H:I | 2023-12-15 | Junaid | 2023-12-15 |  | Junaid | 2023-12-15
Cavan | Net Acquire | 6578c17de7b16 | 2023-12-16 | 2023-12-17 |  | Test NA not printing the ESR | 6.12.145 | 6.12.146 | 2023-12-17 | tested and working fine in local server. A detail vedio is sent by Zyam Dated: 19-12-2023. For more information please refer to mentioned ticket. Please note that this change now will appear in version no. 147. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6578bc5b549e4 | 2023-12-16 | 2023-12-15 |  | HAematology comments not coming across into test NA | 6.12.145 | 6.12.146 | 2023-12-17 | Previously if there were no comments in the NA, the delete query was executing and although if there were any comments that had been delivered from any analyser to the DB it was also deleting from DB. I modified the function of the delete query not to delete if the field is empty in NA and rest of the quires should execute as they were. Please note inset and update queries was not changed as they were working fine and provided a new EXE. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 65784ec519439 | 2023-12-16 | 2023-12-15 |  | Comment not coming across | 6.12.145 | 6.12.146 | 2023-12-17 | Previously if there were no comments in the NA, the delete query was executing and although if there were any comments that had been delivered from any analyser to the DB it was also deleting from DB. I modified the function of the delete query not to delete if the field is empty in NA and rest of the quires should execute as they were. Please note inset and update queries was not changed as they were working fine and provided a new EXE. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6572f7fbceb39 | 2023-12-15 | 2023-12-15 |  | no ward or clinician displaying for a request | 6.12.145 | 6.12.146 | 2023-12-17 | wrote a function that will go to DB of demographics check the GP, Ward and clinician Details if there are any and will populate in the required Field. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6566720521538 | 2023-12-15 | 2023-12-15 |  | Unprinted Micro reports | 6.12.145 | 6.12.146 | 2023-12-17 | This issue is same issue in Ticket No. 6578bc5b549e4 with a slight variation that when we changed the comment function to resolve ticket No. 6578bc5b549e4 there were some logics that were not working due to logical error as they were working previously so I made some variations in the logics and the issue is fixed. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire |  | 2023-12-19 |  |  | Code Optimisation | 6.12.146 | 6.12.147 | 2023-12-19 | Done code optimisation in the code of version No 146 including not to double check with DB to enhance the speed of the EXE, as per the testing in our local server was not showing any signs of slowing the system down however the real environment is live so I hope this issue will be resolved now. | 2023-12-19 | Junaid |  |  | Junaid/Zyam | 2023-12-19
Cavan | Net Acquire | Meeting | 2023-12-21 | 2023-12-21 |  | SampleID should be in the first column of Identification Tab | 6.12.147 | 6.12.148 | 2023-12-21 | When the save/save hold button is clicked it copies the sampleid into the first text box in the identification tab. | 2023-12-21 | Junaid | 2023-12-21 |  | Junaid/Zyam | 2023-12-21
Cavan | Net Acquire | Meeting | 2023-12-22 | 2023-12-22 |  | SampleID should be in the first column of Identification Tab and Saved in Database | 6.12.148 | 6.12.149 | 2023-12-22 | When the save/save hold button is clicked it copies the sampleid into the first text box in the identification tab and when user save the identification, sampleid also saved in the UrineIdent50 table along with the other data if present in the text boxes of identification. | 2023-12-22 | Junaid | 2023-12-22 |  | Junaid/Zyam | 2023-12-22
Cavan | Net Acquire | Meeting | 2023-12-22 | 2023-12-22 |  | Remove log entry | 6.12.148 | 6.12.149 | 2023-12-22 | Log file entry has been stoped. No query which is running in the NetAcquiry exe, is written on the daily log file. | 2023-12-22 | Junaid | 2023-12-22 |  | Junaid | 2023-12-22
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Add a Audit table for UrineIdent50 Table. | 6.12.149 | 6.12.150 | 2023-12-26 | Create a audit table "UrineIdent50Audit" which saves old data of urineIdent50 before updating the results. | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Add log only for Identification | 6.12.149 | 6.12.150 | 2023-12-26 | Allow log entry only for Identification tab. Exe file only save the log of Insert/Update query for UrineIdent50 and UrineIdent50Audit | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Clear memory | 6.12.149 | 6.12.150 | 2023-12-26 | Clear all variables befor loading the Identification data and before saving the identification data. | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Whatsapp | 2023-12-27 | 2023-12-27 |  | Dublicate Result in MicroBiology | 6.12.150 | 6.12.151 | 2023-12-27 | Add delays after saving the Micro results. | 2023-12-27 | Junaid | 2023-12-27 |  | Junaid | 2023-12-27
Cavan | Net Acquire | Whatsapp | 2023-12-28 | 2023-12-28 |  | Dublicate Result in MicroBiology | 6.12.151 | 6.12.152 | 2023-12-28 | Add msgbox after saving Micro results. | 2023-12-28 | Junaid | 2023-12-28 |  | Junaid | 2023-12-28
Cavan | Transfusion | 65363b7c395e3 | 2023-10-23 | 2023-12-29 |  | Current Tranfusion - Adjust Blood Unit Label | 8.0.133 | 8.0.134 | 2023-12-29 | We added a blank line on the top of the lable to push down the text in the required place. | 2023-12-29 | Zyam | 2023-12-29 |  | Junaid | 2023-12-29
Cavan | Net Acquire | 6595205b1ff35 | 2024-01-03 | 2024-01-03 |  | NA Version 152 crashing | 6.12.152 | 6.12.153 | 2024-01-03 | We have removed few function that were storing some junk values in the memory. | 2024-01-03 | Junaid | 2024-01-03 |  | Junaid | 2024-01-03