## Cavan
Client Name | Application | Ticket No. | Ticket Date | Ticket Comp Date | Ticket Close Date | Description | Current Version | Change to Version | Exe Sent Date | Changes | Change Date | Develepor Name | Development Date | Specimen numbers | Tester Name | Tested Date | Appendicies
Cavan | Net Acquire | 6579dbdeef522 | 2023-12-13 | 2023-12-15 |  | Unable to print haem report because GP field populated with 0 | 6.12.145 | 6.12.146 | 2023-12-17 | wrote a function that will go to DB of demographics check the GP Details if there are any and will populate in the required Field+H:I Now the external request is also showing in the NA | 2023-12-15 | Junaid | 2023-12-15 |  | Junaid | 2023-12-15
Cavan | Net Acquire | 6578c17de7b16 | 2023-12-16 | 2023-12-17 |  | Test NA not printing the ESR | 6.12.145 | 6.12.146 | 2023-12-17 | tested and working fine in local server. A detail vedio is sent by Zyam Dated: 19-12-2023. For more information please refer to mentioned ticket. Please note that this change now will appear in version no. 147. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6578bc5b549e4 | 2023-12-16 | 2023-12-15 |  | HAematology comments not coming across into test NA | 6.12.145 | 6.12.146 | 2023-12-17 | Previously if there were no comments in the NA, the delete query was executing and although if there were any comments that had been delivered from any analyser to the DB it was also deleting from DB. I modified the function of the delete query not to delete if the field is empty in NA and rest of the quires should execute as they were. Please note inset and update queries was not changed as they were working fine and provided a new EXE. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 65784ec519439 | 2023-12-16 | 2023-12-15 |  | Comment not coming across | 6.12.145 | 6.12.146 | 2023-12-17 | Previously if there were no comments in the NA, the delete query was executing and although if there were any comments that had been delivered from any analyser to the DB it was also deleting from DB. I modified the function of the delete query not to delete if the field is empty in NA and rest of the quires should execute as they were. Please note inset and update queries was not changed as they were working fine and provided a new EXE. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6572f7fbceb39 | 2023-12-15 | 2023-12-15 |  | no ward or clinician displaying for a request | 6.12.145 | 6.12.146 | 2023-12-17 | wrote a function that will go to DB of demographics check the GP, Ward and clinician Details if there are any and will populate in the required Field. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire | 6566720521538 | 2023-12-15 | 2023-12-15 |  | Unprinted Micro reports | 6.12.145 | 6.12.146 | 2023-12-17 | This issue is same issue in Ticket No. 6578bc5b549e4 with a slight variation that when we changed the comment function to resolve ticket No. 6578bc5b549e4 there were some logics that were not working due to logical error as they were working previously so I made some variations in the logics and the issue is fixed. | 2023-12-15 | Junaid |  |  | Zyam | 2023-12-17
Cavan | Net Acquire |  | 2023-12-19 |  |  | Code Optimisation | 6.12.146 | 6.12.147 | 2023-12-19 | Done code optimisation in the code of version No 146 including not to double check with DB to enhance the speed of the EXE, as per the testing in our local server was not showing any signs of slowing the system down however the real environment is live so I hope this issue will be resolved now. | 2023-12-19 | Junaid |  |  | Junaid/Zyam | 2023-12-19
Cavan | Net Acquire | Meeting | 2023-12-21 | 2023-12-21 |  | SampleID should be in the first column of Identification Tab | 6.12.147 | 6.12.148 | 2023-12-21 | When the save/save hold button is clicked it copies the sampleid into the first text box in the identification tab. | 2023-12-21 | Junaid | 2023-12-21 |  | Junaid/Zyam | 2023-12-21
Cavan | Net Acquire | Meeting | 2023-12-22 | 2023-12-22 |  | SampleID should be in the first column of Identification Tab and Saved in Database | 6.12.148 | 6.12.149 | 2023-12-22 | When the save/save hold button is clicked it copies the sampleid into the first text box in the identification tab and when user save the identification, sampleid also saved in the UrineIdent50 table along with the other data if present in the text boxes of identification. | 2023-12-22 | Junaid | 2023-12-22 |  | Junaid/Zyam | 2023-12-22
Cavan | Net Acquire | Meeting | 2023-12-22 | 2023-12-22 |  | Remove log entry | 6.12.148 | 6.12.149 | 2023-12-22 | Log file entry has been stoped. No query which is running in the NetAcquiry exe, is written on the daily log file. | 2023-12-22 | Junaid | 2023-12-22 |  | Junaid | 2023-12-22
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Add a Audit table for UrineIdent50 Table. | 6.12.149 | 6.12.150 | 2023-12-26 | Create a audit table "UrineIdent50Audit" which saves old data of urineIdent50 before updating the results. | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Add log only for Identification | 6.12.149 | 6.12.150 | 2023-12-26 | Allow log entry only for Identification tab. Exe file only save the log of Insert/Update query for UrineIdent50 and UrineIdent50Audit | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Meeting | 2023-12-26 | 2023-12-26 |  | Clear memory | 6.12.149 | 6.12.150 | 2023-12-26 | Clear all variables befor loading the Identification data and before saving the identification data. | 2023-12-26 | Junaid | 2023-12-26 |  | Junaid | 2023-12-26
Cavan | Net Acquire | Whatsapp | 2023-12-27 | 2023-12-27 |  | Dublicate Result in MicroBiology | 6.12.150 | 6.12.151 | 2023-12-27 | Add delays after saving the Micro results. | 2023-12-27 | Junaid | 2023-12-27 |  | Junaid | 2023-12-27
Cavan | Net Acquire | Whatsapp | 2023-12-28 | 2023-12-28 |  | Dublicate Result in MicroBiology | 6.12.151 | 6.12.152 | 2023-12-28 | Add msgbox after saving Micro results. | 2023-12-28 | Junaid | 2023-12-28 |  | Junaid | 2023-12-28
Cavan | Transfusion | 65363b7c395e3 | 2023-10-23 | 2023-12-29 |  | Current Tranfusion - Adjust Blood Unit Label | 8.0.133 | 8.0.134 | 2023-12-29 | We added a blank line on the top of the lable to push down the text in the required place. | 2023-12-29 | Zyam | 2023-12-29 |  | Junaid | 2023-12-29
Cavan | Net Acquire | 6595205b1ff35 | 2024-01-03 | 2024-01-03 |  | NA Version 152 crashing | 6.12.152 | 6.12.153 | 2024-01-03 | We have removed few function that were storing some junk values in the memory. | 2024-01-03 | Junaid | 2024-01-03 |  | Junaid | 2024-01-03
Cavan | Net Acquire | 6598163fa5534 | 2024-01-05 | 2024-01-08 |  | ID information not sticking | 6.12.153 | 6.12.154 | 2024-01-08 | We have added further checks in the micro procedure that would prevent the issue while maintaining the performance of the exe. | 2024-01-08 | Junaid | 2024-01-08 |  | Junaid | 2024-01-08
Cavan | Net Acquire | Whatsapp | 2024-01-08 | 2024-01-08 |  | Item cannot be found in the collection corresponding to the requested name or ordinal. | 6.12.153 | 6.12.154 | 2024-01-08 | There was a join query executed on SensitivitiesArc and Antibioitcs in which there was a column named 'Archived By'. The value of this column was being assigned but it was't fetched (mentioned). That was why the issue was occurring. | 2024-01-08 | Junaid | 2024-01-08 |  | Junaid | 2024-01-08
Cavan | Net Acquire | Whatsapp | 2024-01-08 | 2024-01-08 |  | String or binary data would be truncated. | 6.12.153 | 6.12.154 | 2024-01-08 | There there is a column in the urineident50 table named 'result' that has a maximum length of 500. This issue was occurred because the length of the string was greater than 500 therefore causing this issue. | 2024-01-08 | Junaid | 2024-01-08 |  | Junaid | 2024-01-08
Cavan | Net Acquire | Whatsapp | 2024-01-08 | 2024-01-08 |  | Incorrect syntax near 'Hea'. | 6.12.153 | 6.12.154 | 2024-01-08 | This issue was caused by an apostrophe in gp's name which was causing this sytax error. We have implemented a user-defined function 'addticks' to fix this issue. | 2024-01-08 | Junaid | 2024-01-08 |  | Junaid | 2024-01-08
Cavan | Net Acquire | Whatsapp | 2024-01-08 | 2024-01-08 |  | Type mismatch | 6.12.153 | 6.12.154 | 2024-01-08 | The data that was being inserted in the db was string type while the data of that respective column was int this is why this error was occurring. We have fixed this by converting the string type variable to int type. | 2024-01-08 | Junaid | 2024-01-08 |  | Junaid | 2024-01-08
Cavan | Net Acquire | 659c10fbe70bc | 2024-01-09 | 2024-01-09 |  | Unable to delete comments | 6.12.154 | 6.12.155 | 2024-01-09 | There was a condtion in function of micro comments save that if the comments are empty then the save query will not be exeucted. We have remevoed that condition and now the comments are deleting. | 2024-01-09 | Junaid/Zyam | 2024-01-09 |  | Junaid/Zyam | 2024-01-09
Cavan | Net Acquire | 659c0e4298a69 | 2024-01-09 | 2024-01-09 |  | Microbiology comments | 6.12.154 | 6.12.155 | 2024-01-09 | There was a condtion in function of micro comments save that if the comments are empty then the save query will not be exeucted. We have remevoed that condition and now the comments are deleting. | 2024-01-09 | Junaid/Zyam | 2024-01-09 |  | Junaid/Zyam | 2024-01-09
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-11 | 2024-01-12 |  | Type mismatch(CheckPrintValidLog) | 6.12.155 | 6.12.156 | 2024-01-09 | This issue occurs when the sampleid is empty. So we have implmented a check that if the sampleid is empty then simply exit the sub. | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Invalid array index | 6.12.155 | 6.12.156 | 2024-01-09 | This has happened due to memory problem, we have remvoed some extra variables that were taking extra space in the memory. | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Invalid use of null | 6.12.155 | 6.12.156 | 2024-01-09 | A null value was being entered into the db. We have removed the null value and sending an empty string instead | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Invalid property array index | 6.12.155 | 6.12.156 | 2024-01-09 | At the first index of an array there was no value and in the code, it was accessing the first index therefore we have removed that function that access the first index | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Error converting data type | 6.12.155 | 6.12.156 | 2024-01-09 | When the sampleid Is null. It simply sends an empty string instead of a 0. There this error occurs. We have added a condition with which the function won't be executed if the sample id is empty | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Error converting varchar datatyppe to small datetime | 6.12.155 | 6.12.156 | 2024-01-09 | We have changed the format of the datetime | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | This key already associated with a element | 6.12.155 | 6.12.156 | 2024-01-09 | We have added a condtion that if the key is already associated then that key is not added to the collection in isolates function | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Invalid use of null | 6.12.155 | 6.12.156 | 2024-01-09 | We have added the function 'Convert Null' That formats the Null to an empty string | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65095c33470af | 2024-01-22 | 2024-01-22 |  | Strange printing of result | 6.12.155 | 6.12.156 | 2024-01-09 | We have inserted printedby and correct datetime for in the db | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Type Mismatch (Micro) | 6.12.155 | 6.12.156 | 2024-01-09 | We have removed the function sysOptMicroOffSet that format the micro sampleid. | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Incorrect syntax near 'really' | 6.12.155 | 6.12.156 | 2024-01-09 | This error occurred because there was a single quote in the name. Now we have made a function that will prevent this issue from occurs | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Invalid use of datetime contrl | 6.12.155 | 6.12.156 | 2024-01-09 | The error was occuring due a format of a datetime. Now we are simply sending current date in correct format | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-22 | 2024-01-22 |  | Error converting data type(SampleID) | 6.12.155 | 6.12.156 | 2024-01-09 | When the sampleid Is null. It simply sends an empty string instead of a 0. There this error occurs. We have added a condition with which the function won't be executed if the sample id is empty | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6778acd9dc | 2024-01-11 | 2024-01-12 |  | Overflow | 6.12.155 | 6.12.156 |  | This has happened due to memory problem, we have remvoed some extra variables that were taking extra space in the memory. | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | Net Acquire | 65a6f641c63b6 | 22/01/24 | 22/01/24 |  | Discipline showing in WE | 6.12.156 | 6.12.157 |  | We have added a check that if the the comment field in empty in NA and there are comments in db against that sample id then the comments aren't updated.
Cavan | Net Acquire | 659ad4b5ca157 | 2024-01-11 | 2024-01-12 |  | Changing receipt time of Potassium | 6.12.156 | 6.12.157 |  | We have updated the Potassium receipt time from 8 hours to six hours | 22/01/24 | Junaid | 22/01/24 |  | Junaid | 22/01/24
Cavan | BloodTransfusion | 65363b7c395e3 | 2024-01-11 | 2024-01-12 |  | Blood tranfusion Label | 8.0.0.134 | 8.0.0.135 |  | Blood tranfusion label has been pulled down by modifying the function that prints the label (adding 2 new lines above label) | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Cavan | BloodTransfusion | 65363b7c395e3 | 2024-01-11 | 2024-01-12 |  | Blood tranfusion Label | 8.0.0.135 | 8.0.0.136 |  | Ocm changes have been removed (Product order message box) | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Cavan | BloodTransfusion | 65363b7c395e3 | 2024-01-11 | 2024-01-12 |  | Blood tranfusion Label | 8.0.0.136 | 8.0.0.137 |  | Blood tranfusion label has been pulled down by modifying the function that prints the label (adding 2 new lines above label) | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Cavan | BloodTransfusion | 65363b7c395e3 | 2024-01-11 | 2024-01-12 |  | Blood tranfusion Label | 8.0.0.137 | 8.0.0.138 |  | There were mainly 2 issues. 1- When the result was saved, the lab number field clears which shouldn't happen, 2-A messagebox popup appears when we save a new request which shouldn't be display. Both of the issues has been fixed. | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Cavan | Net Acquire | 65b24df50df35 | 25-01-24 | 28/01/24 |  | Plausible values incorrect coag results | 6.12.157 | 6.12.158 |  | We have added conditions in the condition that adds 'XXXX' in place of result if the result is outside of Plausible Range | 28/01/24 | Junaid | 28/01/24 |  | Junaid | 28/01/24
Cavan | LabLink | Whatsapp | 24-01-24 | 25/01/24 |  | Path was not changing. | 3.1.0.6 | 3.1.0.7 |  | There was a syntax error in the query that stores the path in the db. We have modifed the function and it is working fine now. | 28/01/24 | Junaid | 28/01/24 |  | Junaid | 28/01/24
Cavan | Net Acquire | 65b0f1863d8cb | 24-01-24 | 28/01/24 |  | New netacquire releases not functioning in Microbiology | 6.12.157 | 6.12.158 |  | We have modifed the date format in the "Load all details" function and this issue is fixed | 28/01/24 | Junaid | 28/01/24 |  | Junaid | 28/01/24
Cavan | LabLink | 65b0f1863d8cb | 25-01-24 | 28/01/24 |  | Lablink in test is not creating test files | 3.1.0.7 | 3.1.0.8 |  | We have modified the query that fetches the outstanding request. | 28/01/24 | Junaid | 28/01/24 |  | Junaid | 28/01/24
Cavan | Net Acquire | 65bb734982080 | 24-01-24 | 28/01/24 |  | updating age ranges in haemtology lists menu | 6.12.158 | 6.12.159 |  | There was a logical error in the code when we click the "AddNew" button. We have fixed the logical error and now the enteries are coming through | 28/01/24 | Junaid | 28/01/24 |  | Junaid | 28/01/24
Cavan | Net Acquire | 65b90d48d3c0d | 30/1/24 | 2024-06-02 |  | Baby age displaying in years instead of days in NA | 6.12.159 | 6.12.160 |  | There was a logical error in the code that was causing this issue. We have fixed the logical error and now the age will be correct. | 2024-06-02 | Zyam | 2024-06-02 |  | Zyam | 2024-06-02
Cavan | Net Acquire | 659d575666d7f | 2024-09-01 | 2024-06-02 |  | 9367157 - no longer a ward displaying ¦ SampleID 9367157 | 6.12.159 | 6.12.160 |  | According to the instruction provided by Ken, we have removed the function that fetches the ward from PatientIfs which was causing this issue. Now the ward will be fetched from the demographics against the given sampleid. This is fixed in version NA version 160. | 2024-06-02 | Junaid | 2024-06-02 |  | Junaid | 2024-06-02
Cavan | Net Acquire | 65b24df50df35 | 25-01-24 | 2024-07-02 |  | Plausible values incorrect coag results | 6.12.160 | 6.12.161 |  | Previiously, it wasn't working for same cases. Therefore, we have modified the condition entirely that is reponsible for hiding the result when it is outside of plausible ranges and it working fine now, | 2024-07-02 | Junaid | 2024-07-02 |  | Junaid | 2024-07-02
Cavan | Net Acquire | 65c5dc3bc93a6 | 2024-09-02 | 2024-12-02 |  | remove button from netacquire screen ¦ SampleID 21172347 | 6.12.161 | 6.12.162 |  | We have removed the button "Order External Reports" from external order screen | 2024-12-02 | Junaid | 2024-12-02 |  | Junaid | 2024-12-02
Cavan | Net Acquire | 65c4f62799875 | 2024-08-02 | 2024-12-02 |  | Netacquire time error ¦ Patient - n/a | 6.12.161 | 6.12.162 |  | This might be occuring due to sample time not being properly loaded when the print button is clicked. We have added a function that will make sure the sample time is loaded properly before printing in NA exe 162. | 2024-12-02 | Junaid | 2024-12-02 |  | Junaid | 2024-12-02