## Sheet1
OCM Tidy Up | Issue/Action | Additional Comments | MRN | Update
Patient History
OCM BT | Remove |  |  | Completed
Batch request | Remove | when was this deployed |  | Completed
Critical List | Remove | when was this deployed |  | Completed
Messaging | Remove | when was this deployed |  | Completed
Patient Audit
User mapping
User Levels
Issues with OCM
Ward Requiry | External results not displaying for both OCM and paper request |  | 253829 | Unable to test in test
| External results list only shows paper requests sampleID | Does this list pull everything on the patient or just 35 days. | 253829 | Unable to test in test
| External and Biochemistry Cumulative | Shows the external results | 253829 | Unable to test in test
| View Scan for paper externals | Not functioning | 253829 | Unable to test in test
| Download report on OCM numbers not working |  |  | Completed
| View Request not working | What is it, what is it suppose to do. |  | Completed
| Speed Issue | Cumulatives especially | 105870 | Need to test in Live
| Printed Report | No functionality to print | 253829 | Completed
| BT Cumulative Remove from dropdown | Remove, this is not working | 253829 | Completed
| Remove ALL from cumulative dropdown | Remove, this is not working | 253829 | Completed
Labels
| Issue with browser settings |  |  | Will monitor but looks ok
| 01DDMMYY |  |  | Not done
| Reprint labels does not open print review. Ctrl +P | Should not be able to reprint labels in OCM, functioality should only be in LIMS |  | Unable to test as it is in ocmtest2
Sample Collection
| Back button on Phlebotomy page | Not taking the user back to the collection list. |  | Completed
| Issues with speed of printing | taking too long to go from Generate barcode to print preview |  | Completed
| Issues with scanning Barcodes | barcode already scanned error message |  | Completed
Log in
| Log in on another device when user is not |  |  | Has not happened in test today will monitor
LIMS
| Scanning in of SampleID | Extremely slow. SampleId 90007816 FBC after 5 minutes of spinning. Refresh screen and scanned again |  | Seems to be faster. Need to monitor in Live
| Delay in requests going into AMS and EPU | takes up to 20 minutes |  | Can only test in Live
| OCM externals | Having to print an external form for Biomnis |  | Test in Live
| Scan Request |  |  | Completed
| OCM paper request form CC duplicate GP | Ticket raised 90007816 |  | Tested, Save button not working on Demographic screen. Ticket raised