## TullaMore (Zyaeem)
Client Name | Application | Ticket No. | Ticket Date | Description | Current Version | Change to Version | Changes | Change Date | Develepor Name | Development Date | Specimen numbers | Tester Name | Tested Date | Appendicies
TullaMore | Genexpert | 65548da1dbed0 | 2023-11-15 | Link Genexpert Second Analyzer |  |  | Linked Genexpert Second Analyzer |  | Junaid |  |  | Junaid
TullaMore | Histology | 65661decc6d9a, 653b6594e63fe | 2023-10-27 | Dart View button & save issue |  | 1.2.0.43 | Dart viewer button added & save is fix |  | Junaid |  |  | Junaid
TullaMore | Ward Enquiry | Whatsapp/Email | 2023-10-30 | Unnecssary buttons & Tabs |  | 1.2.0.78 | Removed Unnecssary buttons & Tabs & changed the path of dart viewer |  | Junaid |  |  | Junaid
TullaMore | Netacquire | 656f2c4c5bdff | 2023-12-05 | Path of Dart Viewer |  | 6.11.0.7 | Changed the path of Dart Viewer |  | Junaid |  |  | Junaid
Tullamore | Blood Tranfusion | 656f2c4c5bdff | 2023-05-12 | Changed Dart Viewer Path | 7.5.0.18 | 7.5.0.19 | Updated Dart Viewer Path | 18/12/2023 | Zyam | 18/12/2023 |  | Zyam | 18/12/2023
Tullamore | Histology | 653b6594e63fe | 27/10/23 | Added DartViewer to all rows in Search | 2.10.0.51 | 2.10.0.52 | Added DartViewer to all the rows in search | 18/12/2023 | Zyam | 18/12/2023 |  | Zyam | 18/12/2023
Tullamore | PrintHandler | 6548a8ea07e40 | 2023-06-11 | Insufficient character space to allow full reporting of tests in Microbiology - see attachment. This fix is required urgently to facilitate accurate reporting of test results. Contact Oliver Cleary 0877947027. | 2.10.0.118 | 2.10.0.119 | Previously, the number of antibiotics that needs to display were being fetched from Options table. Now we have removed that limit and all of the antibiotics will be printed. Furthermore, we have added another line that would be used to display the full report | 15/12/23 | Zyam | 15/12/23 |  | Zyam | 15/12/23
Tullamore | Blood Tranfusion | #656f2c4c5bdff | 2023-05-12 | Error while opening transfusion | 7.5.0.19 | 7.5.0.20 | The error was due to connection not being developed with Database due to an incorrect password correct. We have corrected it and exe is delivered | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Tullamore | NetAcquire | 65952ab20d484 | 2024-04-01 | Update EGFR Formula | 6.10.0.267 | 6.10.0.268 | EGFR formula is updated for each gender | 2024-04-01 | Zyam | 2024-04-01 |  | Zyam | 2024-04-01
Tullamore | Histology | 653b6594e63fe | 27/10/2023 | Error while opening DartViewer | 2.10.0.52 | 2.10.0.53 | Added DartViewer on double click instead of a single click to fix the error click to fix the error | 2024-08-01 | Zyam | 2024-08-01 |  | Zyam | 2024-08-01
Tullamore | Histology | 653b6594e63fe | 27/10/2023 | Error while opening DartViewer(To many parameters supplied) | 2.10.0.52 | 2.10.0.53 | he issue was occurring due to blank spaces between the case ID The caseid string has been formated. click to fix the error | 2024-08-01 | Zyam | 2024-08-01 |  | Zyam | 2024-08-01
Tullamore | PrintHandler | 6548a8ea07e40 | 2023-06-11 | Comments not showing properly | 2.10.0.119 | 2.10.0.120 | There was an empty line after the first organisn while the loop exectes that was causing this problem. | 2024-11-01 | Zyam | 2024-11-01 |  | Zyam | 2024-11-01
Tullamore | PrintHandler | 6548a8ea07e40 | 2023-06-11 | Word are splitting on two different lines | 2.10.0.120 | 2.10.0.121 | Word wrap feature has been added therefore words aren't splitting on two lines | 13/1/2024 | Zyam | 13/1/2024 |  | Zyam | 13/1/2024
Tullamore | PrintHandler | 6548a8ea07e40 | 2023-06-11 | Word are splitting on two different lines, unncesscary gap between word and Authorised by are not displaying | 2.10.0.121 | 2.10.0.122 | We have made a new algorithm in the print organism function that prevents the words splitting and make sure no unnncesasry spaces should be in the name. Furthermore, we have also fixed authorised by for Bio, Coag, Haem, End, Imm. | 13/1/2024 | Zyam | 13/1/2024 |  | Zyam | 13/1/2024
Tullamore | PrintHandler | 6548a8ea07e40 | 2023-06-11 | Organism name not printing correctly. | 2.10.0.122 | 2.10.0.123 | We have adjusted the length of the organism line printing | 16/1/2024 | Zyam | 16/1/2024 |  | Zyam | 16/1/2024
Tullamore | NetAcquire | Via Whatsapp | 22/01/2024 | External order screen type mismatch error | 6.10.0.268 | 6.10.0.269 | The nodes that were in the tree view were not defined. We have defined them as Mscomctl.Node type at every point when a node is made | 22/01/2024 | Zyam | 22/01/2024 |  | Zyam | 22/01/2024
Tullamore | NetAcquire | 656f2c4c5bdff | 22/01/2024 | however micro are having an issue with the reporting of results and subsequent issue to ward enquiry - please see attached. Ultan Smith is the contact for this, he can explain the problem – 0579358390. Happy to have a zoom meeting to discuss. Michelle | 6.10.0.269 | 6.10.0.270 | There was condition in the code that was responsible for poping up the message box. The function has been modified and it is working as expeced now | 25/01/2024 | Zyam | 25/01/2024 |  | Zyam | 25/01/2024
Tullamore | NetAcquire | 6548a8ea07e40 | 2023-06-11 | Release to Ward/GP | 6.10.0.270 | 6.10.0.271 | The problem appears to be in NA instead of Printhandler (discussed with Ken). We have modified the function in such a way that we have removed the pop up that appears after we validate the result. As long as the release to ward/gp button is not clicked, the report is not released to Ward/GP. | 31/1/2024 | Zyam | 31/1/2024 |  | Zyam | 31/1/2024
Tullamore | NetAcquire | 6548a8ea07e40 | 2023-06-11 | Bioresults audit not visible | 6.10.0.270 | 6.10.0.271 | We have changed the form onlaod function of the Audit form that defines the format of the rtb text shown in the text box of audit. Now the biochemistry audit are visible | 31/1/2024 | Zyam | 31/1/2024 |  | Zyam | 31/1/2024
Tullamore | Ipms | 65b2788bd9e1f | 25/01/2024 | MRHT iPMS TEST Interface | 1.0.0.5 | 1.0.0.6 | When we open the current exe running in Live system, it shows a error message which shows the db connection is failing. We have modified a connection function in which the exe is successfully developing a connection to db. | 31/1/2024 | Zyam | 31/1/2024 |  | Zyam | 31/1/2024
Tullamore | NetAcquire | 6548a8ea07e40 | 2023-06-11 | Plot date issue is only limited to 7 days | 6.10.0.270 | 6.10.0.271 | Plot date from and to has been extended to as far as 6 months depending on the sample id history | 2024-01-02 | Zyam | 2024-01-02 |  | Zyam | 2024-01-02
Tullamore | NetAcquire | 6548a8ea07e40 | 2023-06-11 | Report header incorrect | 2.10.0.123 | 2.10.0.124 | The header of the report is corrected as "MRH @ Tullamore" | 2024-07-02 | Zyam | 2024-07-02 |  | Zyam | 2024-07-02
Tullamore | Histology | 653b6594e63fe | 27/10/2023 | Can't type Caseid into the Worksheet | 2.10.0.53 | 2.10.0.54 | There was an undefined function LS() that was firing an error when the case id is typed into the field. Therefore, we have defined a new a function named LS() that has resolved the issue. | 19/02/2024 | Zyam | 19/02/2024 |  | Zyam | 19/02/2024
Tullamore | Ipms | 65b2788bd9e1f | 25/01/2024 | MRHT iPMS TEST Interface | 1.0.0.6 | 1.0.0.7 | There was a connection error when trying to connect to test DB. This issue has been fixed in version 1.0.0.7 | 22/2/2024 | Zyam | 22/2/2024 |  | Zyam | 22/2/2024
Tullamore | Histology | 653b6594e63fe | 27/10/2023 | Not being able to enter gender | 2.10.0.54 | 2.10.0.55 | There was an undefined function LS() that was firing an error when we click on the gender field. We have changed the functionality of the onclick of gender field. | 27/2/2024 | Zyam | 27/2/2024 |  | Zyam | 27/2/2024
Tullamore | GeneExpert | 65548da1dbed0 | 15/11/2023 | Subject : MRHT Micro - Interface second Gene Expert Analyser |  | 1.0.0 | We have interfaced a second geneexpert interface. Furthermore, the error regarding saving ip and port Is also fixed. | 2024-04-03 | Zyam | 2024-04-03 |  | Zyam | 2024-04-03
TullaMore | Ward Enquiry | Email | 2024-03-04 | Tranfusion Module in Ward Enquiry | 1.2.0.78 | 1.2.0.79 | we have implemented transfusion module of Mullingar in ward enquiry | 2024-05-04 | Zyam | 2024-05-04 |  | Zyam | 2024-05-04
TullaMore | PrintHandler | 661fd1cba94bb | 17/4/2024 | Print Handler | 2.10.0.123 | 2.10.0.124 | We have implemented exception handling in PrintFooterRTB function which was mainly responsible for printing authorised Name on the report which has resolved the error | 17/4/2024 | Zyam | 17/4/2024 |  | Zyam | 17/4/2024

## Tulla More Web Application
Application Type | Application Name | Client Name | Deployment Date | Version | Developer | Changes From | Ticket IDs | Description
Web Application | Histology | Tullamore, Cavan |  | 1.0.3 | Hamza Ayub, Zain Tahir,Zyam |  |  | 1)Histology
Web Application | Lims,Histology | (Cavan),(Tullamore, Cavan) |  | 1.0.0 | Hassan |  |  | 1)Lims dashboard issue resolved. 2) Mapping issue resolved.
Web Application | Histology | Tullamore, Cavan |  | 1.0.0 | Hassan Ahmad |  |  | 1) Added slides/nodes in worksheet interface.
Web Application | Histology | Tullamore,Cavan |  | 1.0.3 | Zain, Hamza |  |  | 1)Worked on worksheets.